## Product Backlog
NovaCart AI Customer Support Chatbot — Product Backlog
Simulated Agile/Scrum backlog for portfolio demonstration
Story ID | Epic ID | Epic | Story Title | User Story | Priority | Release | Story Points | Sprint | Requirement ID | Status | Owner | Dependency / Notes
US-001 | EP-01 | Intent & Conversation | Identify Customer Intent | As a customer, I want the chatbot to understand what I am asking, so that I receive the appropriate support. | Must | MVP | 5 | Sprint 1 | FR-001 | Not Started | AI/ML Team | Intent classification
US-002 | EP-01 | Intent & Conversation | Clarify Customer Request | As a customer, I want the chatbot to ask a clarification question when my request is unclear, so that I can provide the information needed to resolve my issue. | Must | MVP | 3 | Sprint 1 | FR-002 | Not Started | AI/ML Team | US-001
US-003 | EP-01 | Intent & Conversation | Collect Missing Information | As a customer, I want the chatbot to ask for missing information, so that it can complete my request accurately. | Must | MVP | 3 | Sprint 1 | FR-002 | Not Started | Engineering | US-001
US-004 | EP-02 | Self-Service Support | Check Order Status | As a customer, I want to check my order status through the chatbot, so that I can get an update without contacting a support agent. | Must | MVP | 8 | Sprint 2 | FR-003 | Not Started | Engineering | Order Management API
US-005 | EP-02 | Self-Service Support | Check Delivery ETA | As a customer, I want to know the expected delivery date of my order, so that I understand when I should expect my package. | Must | MVP | 5 | Sprint 2 | FR-003 | Not Started | Engineering | Order Management API
US-006 | EP-02 | Self-Service Support | Get Return Policy Information | As a customer, I want to ask the chatbot about NovaCart's return policy, so that I can understand the applicable return rules without contacting an agent. | Must | MVP | 3 | Sprint 2 | BR-003 / FR-004 | Not Started | Knowledge Management | Approved return policy
US-007 | EP-02 | Self-Service Support | Get Password Reset Guidance | As a customer, I want to receive password-reset guidance through the chatbot, so that I can regain access to my account without contacting support. | Must | MVP | 3 | Sprint 2 | FR-004 | Not Started | Engineering | Authentication service
US-008 | EP-02 | Self-Service Support | Get Product Information | As a customer, I want to ask questions about products, so that I can quickly find approved product information. | Must | MVP | 5 | Sprint 2 | BR-003 / FR-004 | Not Started | Knowledge Management | Approved product content
US-009 | EP-03 | Customer Authentication | Authenticate Customer | As a customer, I want my identity to be verified before account-specific information is provided, so that my personal information remains protected. | Must | MVP | 8 | Sprint 2 | NFR-002 | Not Started | Engineering | Authentication service
US-010 | EP-03 | Customer Authentication | Protect Customer Information | As a customer, I want the chatbot to expose only the information required to answer my request, so that unnecessary personal information is not disclosed. | Must | MVP | 5 | Sprint 2 | BR-005 / NFR-002 | Not Started | Security | US-009
US-011 | EP-04 | Human Handoff | Request Human Agent | As a customer, I want to request a human support agent, so that I can receive assistance when the chatbot cannot resolve my issue. | Must | MVP | 5 | Sprint 3 | BR-005 / FR-005 | Not Started | CRM Team | CRM integration
US-012 | EP-04 | Human Handoff | Escalate Complex Issues | As a support agent, I want complex or high-risk customer issues to be escalated to me, so that cases requiring human judgment are handled appropriately. | Must | MVP | 5 | Sprint 3 | BR-005 / FR-005 | Not Started | Support / CRM | US-011
US-013 | EP-04 | Human Handoff | Receive Conversation Context | As a support agent, I want to receive the customer's chatbot conversation history and relevant context, so that I do not need to ask the customer to repeat information. | Must | MVP | 5 | Sprint 3 | FR-006 | Not Started | CRM Team | US-011
US-014 | EP-05 | Knowledge & AI Guardrails | Use Approved Knowledge | As a customer, I want chatbot answers about policies and FAQs to come from approved information, so that I receive reliable and consistent information. | Must | MVP | 5 | Sprint 2 | BR-003 / FR-004 | Not Started | Knowledge Management | Knowledge base
US-015 | EP-05 | Knowledge & AI Guardrails | Prevent Unsupported Responses | As a Product Manager, I want the chatbot to avoid providing unsupported information, so that customers are not given incorrect policies, prices, or eligibility decisions. | Must | MVP | 5 | Sprint 3 | BR-003 / BR-006 | Not Started | AI/ML Team | US-014
US-016 | EP-05 | Knowledge & AI Guardrails | Handle Low Confidence | As a customer, I want the chatbot to acknowledge when it does not understand my request, so that I am guided toward clarification or human support. | Must | MVP | 3 | Sprint 3 | FR-001 / FR-002 / FR-005 | Not Started | AI/ML Team | US-002
US-017 | EP-05 | Knowledge & AI Guardrails | Handle System Failure | As a customer, I want an appropriate fallback when a required business system is unavailable, so that I am not given incorrect information. | Must | MVP | 5 | Sprint 3 | FR-007 | Not Started | Engineering | US-004 / US-005
US-018 | EP-06 | Analytics & Feedback | Capture Interaction Data | As a Data/BI Analyst, I want chatbot interactions and outcomes to be captured, so that chatbot performance and business KPIs can be measured. | Must | MVP | 5 | Sprint 3 | FR-008 / BR-007 | Not Started | Data/BI | Analytics data model
US-019 | EP-06 | Analytics & Feedback | Capture Customer Feedback | As a Product Manager, I want customers to provide feedback after chatbot interactions, so that customer satisfaction and improvement opportunities can be monitored. | Should | MVP | 3 | Sprint 4 | BR-008 | Not Started | Product / BI | US-018
US-020 | EP-06 | Analytics & Feedback | Monitor Chatbot KPIs | As a Support Manager, I want to monitor chatbot resolution, escalation, response time, CSAT, and deflection metrics, so that I can evaluate business outcomes. | Must | MVP | 5 | Sprint 4 | BR-010 | Not Started | Data/BI | US-018
US-021 | EP-02 | Self-Service Support | Check Refund Status | As a customer, I want to check the status of my refund, so that I do not need to contact a support agent for a routine update. | Phase 2 | Phase 2 | 8 | Backlog | — | Backlog | Engineering | Refund system integration
US-022 | EP-02 | Self-Service Support | Check Cancellation Eligibility | As a customer, I want to know whether my order can be cancelled, so that I understand my available options before contacting support. | Phase 2 | Phase 2 | 8 | Backlog | — | Backlog | Engineering | Cancellation rules/API
US-023 | EP-02 | Self-Service Support | Account Support | As a customer, I want assistance with common account-related requests, so that I can resolve routine account issues through self-service. | Phase 2 | Phase 2 | 8 | Backlog | — | Backlog | Engineering | Authentication + account services

## Backlog Summary
Backlog Summary
Metric | Value
Total Stories | 23
MVP Stories | 20
Phase 2 Stories | 3
Must Have | 19
Should Have | 1
MVP Story Points | 94
Planned Sprints | 4

## Sprint View
Sprint | Focus | Stories | Story Points | Outcome
Sprint 1 | Conversation foundation | US-001 to US-003 | 11 | Intent, clarification and information collection
Sprint 2 | MVP self-service | US-004 to US-010, US-014 | 39 | Core self-service, authentication and approved knowledge
Sprint 3 | Escalation, guardrails & analytics | US-011 to US-018 | 40 | Human handoff, guardrails, fallback and analytics capture
Sprint 4 | Feedback & KPI reporting | US-019 to US-020 | 8 | Feedback and management KPI visibility

## Read Me
Purpose | Jira-style product backlog for the simulated NovaCart AI Customer Support Chatbot.
Prioritization | Must/Should/Phase 2 reflects the agreed MVP scope and business priority.
Story Points | Illustrative relative estimates for portfolio demonstration; not actual delivery estimates.
Traceability | Requirement IDs link backlog items to the Requirements and RTM stage.
Status | MVP items begin as Not Started; Phase 2 items remain in Backlog.
Portfolio disclaimer | NovaCart and all backlog estimates are fictional/simulated.