## Defect Log
Defect ID | Test Case ID | Requirement ID | User Story ID | Defect Summary | Description | Severity | Priority | Expected Result | Actual Result | Environment | Reported Date | Assigned To | Status | Root Cause | Resolution | Retest Result | Closed Date | Comments

## Sample Defects
Defect ID | Test Case ID | Requirement ID | User Story ID | Defect Summary | Description | Severity | Priority | Expected Result | Actual Result | Environment | Reported Date | Assigned To | Status | Root Cause | Resolution | Retest Result | Closed Date | Comments
DEF-EX-001 | UAT-004 | FR-003 | US-004 | Order status response returns stale status | For a valid order, the chatbot displayed an outdated order status instead of the latest value returned by the order system. | High | High | Chatbot displays the current authorized order status. | Chatbot displayed a previous status value. | UAT / Mock Order API | 2026-07-08 | Engineering | Fixed | Mock API response mapping did not refresh the status field. | Updated response mapping and added refresh validation. | Pass | 2026-07-10 | Simulated portfolio example; not a real production defect.
DEF-EX-002 | UAT-011 | NFR-002 | US-009 | Failed authentication exposes protected field | A failed authentication scenario returned a protected account field in the chatbot response. | Critical | Critical | Protected information is not displayed when authentication fails. | Protected field was visible after failed authentication. | UAT / Test Account | 2026-07-09 | Engineering | Closed | Authorization check was applied after response construction. | Moved authorization validation before protected-field retrieval. | Pass | 2026-07-11 | Simulated portfolio example; illustrates a security-critical UAT finding.
DEF-EX-003 | UAT-014 | FR-005 | US-012 | Complex complaint is not escalated | A complaint classified as complex remained in the chatbot flow instead of being routed to a human agent. | Critical | High | Complex complaints are escalated to a human agent. | Chatbot continued self-service flow. | UAT / Conversation Test | 2026-07-10 | AI/ML Team | Retest | Escalation rule did not include one complex-complaint intent variant. | Expanded escalation rule and added regression scenario. | Not Retested |  | Simulated portfolio example.
DEF-EX-004 | UAT-017 | BR-003 | US-015 | Unsupported policy statement generated | The chatbot produced a policy statement that was not present in the approved knowledge base. | Critical | High | Unsupported policy information is not generated; the chatbot uses approved knowledge or escalates. | An unsupported policy statement was generated. | UAT / Knowledge Base | 2026-07-10 | AI/ML Team | Fixed | Fallback generation path was not sufficiently constrained to approved content. | Added knowledge-grounding validation and fallback-to-escalation behavior. | Pass | 2026-07-12 | Simulated portfolio example.
DEF-EX-005 | UAT-021 | FR-008 | US-018 | Escalation reason missing from analytics | The interaction record captured escalation but did not capture the reason for escalation. | Medium | Medium | Analytics capture escalation status and reason. | Escalation reason field was blank. | UAT / Analytics | 2026-07-11 | Data/BI | Closed | Escalation event schema omitted the reason attribute. | Added escalation_reason field and updated validation. | Pass | 2026-07-13 | Simulated portfolio example.

## Defect Summary
Defect Management Summary
Purpose | Execution-ready summary for UAT defect tracking. Counts are driven from the Defect Log sheet.
Severity | Count | Status | Count
Critical |  | New
High |  | Assigned
Medium |  | In Progress
Low |  | Fixed
Retest
Closed
Retest Result | Count | Open Defects
Not Retested |  | Critical Defects
Pass
Fail

## Defect Lifecycle
Stage | Meaning | Typical BA / Team Action
New | Defect identified during testing. | Log defect with evidence, severity, priority and traceability.
Assigned | Owner identified. | Assign to the responsible team and confirm impact.
In Progress | Defect is being investigated/fixed. | Analyze root cause and implement correction.
Fixed | Development team reports correction complete. | Prepare for tester/BA retest.
Retest | Correction is being validated. | Execute the original scenario and regression checks.
Closed | Retest passed and evidence is accepted. | Close defect and update traceability.
Reopened | Retest failed or issue persists. | Return to investigation/fix cycle.

## Read Me
Defect Log — Read Me
Purpose | Track UAT defects from discovery through resolution and retest.
Portfolio Context | This is a simulated Business Analyst portfolio project for the fictional NovaCart e-commerce company.
Main Log | The 'Defect Log' sheet is intentionally execution-ready and contains blank rows for actual UAT execution.
Sample Data | The 'Sample Defects' sheet contains illustrative simulated examples only. They are not real production defects or employment results.
Severity | Critical = security, major business risk, or release-blocking issue; High = major functional/business impact; Medium = moderate impact; Low = minor impact.
Priority | Indicates urgency for resolution based on business/release impact.
Traceability | Each defect can be linked back to a UAT test case, requirement and user story.
Lifecycle | New → Assigned → In Progress → Fixed → Retest → Closed. Failed retests may move to Reopened.
BA Interview Point | A BA uses the defect log to maintain traceability, prioritize business impact, coordinate resolution, support retesting, and ensure release readiness.