## Requirements
Requirement ID | Type | Requirement | Priority | Business Objective | Source / Stakeholder | Acceptance / Validation Criteria | User Story ID | Test Case ID | Status
BR-001 | Business | The chatbot shall automate suitable Tier-1 customer-support interactions identified as high-volume and lower-complexity use cases. | Must | Reduce repetitive support workload | Support Manager / BA | Approved MVP intents are available through chatbot. | US-001 | TC-001 | Approved
BR-002 | Business | The chatbot shall provide 24/7 self-service for supported scenarios. | Must | Improve response time and self-service | Customers / Product Manager | Supported intents are accessible outside agent operating hours. | US-002 | TC-002 | Approved
BR-003 | Business | The chatbot shall use approved and maintained knowledge sources for customer-facing responses. | Must | Maintain response accuracy | Knowledge Management / Security | Responses for supported FAQs can be traced to approved knowledge content. | US-003 | TC-003 | Approved
BR-004 | Business | The chatbot shall support human escalation for complex, unsupported, low-confidence or customer-requested cases. | Must | Maintain customer experience | Support Agents / Product Manager | Eligible conversations can be transferred to a human agent. | US-004 | TC-004 | Approved
BR-005 | Business | The chatbot shall capture interaction data required for performance and business KPI reporting. | Should | Measure chatbot performance | Data/BI / Operations | Required KPI fields are captured for each chatbot interaction. | US-005 | TC-005 | Approved
FR-001 | Functional | The chatbot shall identify the customer's intent from the supported intent catalogue. | Must | Automate suitable Tier-1 interactions | BA / AI-ML / Support | Supported sample utterances are mapped to the correct intent. | US-006 | TC-006 | Approved
FR-002 | Functional | The chatbot shall ask a clarification question when required information is missing or the intent cannot be confidently determined. | Must | Improve resolution and reduce incorrect responses | Support Agents / AI-ML | Bot requests the missing information instead of guessing. | US-007 | TC-007 | Approved
FR-003 | Functional | The chatbot shall retrieve authorized order information such as order status and delivery ETA through the order-management integration. | Must | Improve self-service | Engineering / CRM / Product | Authenticated customer receives the correct order information. | US-008 | TC-008 | Approved
FR-004 | Functional | The chatbot shall provide approved responses for FAQ scenarios such as return policy and product information. | Must | Improve self-service | Knowledge Management | FAQ response matches approved source content. | US-009 | TC-009 | Approved
FR-005 | Functional | The chatbot shall pass conversation history and relevant context to the human agent during escalation. | Must | Improve agent productivity | Support Agents / CRM | Agent receives customer query, intent and relevant conversation context. | US-010 | TC-010 | Approved
FR-006 | Functional | The chatbot shall provide a controlled fallback when an integration or supported service is unavailable. | Must | Maintain reliable customer experience | Engineering / IT | Customer receives a clear fallback message and escalation option. | US-011 | TC-011 | Approved
NFR-001 | Non-Functional | Standard supported chatbot responses should be returned within 10 seconds under normal operating conditions. | Should | Improve response time | Product Manager / Operations | Performance test meets the agreed response-time threshold. | US-012 | TC-012 | Approved
NFR-002 | Non-Functional | The solution shall protect customer information using appropriate authentication, access control and minimum-necessary data exposure. | Must | Protect customer data | IT/Security | Unauthorized users cannot access protected customer/order information. | US-013 | TC-013 | Approved
NFR-003 | Non-Functional | The chatbot should be available 24/7 for supported customer interactions, subject to planned maintenance and service availability. | Should | Provide 24/7 support | Product / Engineering | Availability monitoring confirms agreed service target. | US-014 | TC-014 | Approved
BRULE-001 | Business Rule | The chatbot must not invent policies, prices, eligibility rules or unsupported information. | Must | Maintain response accuracy | Knowledge Management / Security | Unsupported information is not presented as fact. | US-015 | TC-015 | Approved
BRULE-002 | Business Rule | Complex complaints, high-risk cases and sensitive investigations shall be routed to human support rather than autonomously resolved. | Must | Maintain customer experience and risk control | Support Manager / Security | Defined high-risk scenarios trigger human handoff. | US-016 | TC-016 | Approved

## Traceability Summary
Traceability Level | Mapped To
Business Objective | Requirement ID
Requirement ID | User Story ID
User Story ID | Test Case ID
Test Case ID | UAT Result / Defect
Purpose | Demonstrate end-to-end requirements traceability from business need to validation

## MoSCoW Guide
Priority | Meaning | Use in Project
Must | Essential for MVP | Required for a usable and safe chatbot MVP
Should | Important but not critical | High-value capability that can follow core MVP delivery
Could | Nice to have | Lower-priority enhancement
Won't | Not planned for current scope | Explicitly deferred from current release